## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2025-04-01 |  |  |  |  | April | [34 empty] | May
Scrolling Increment: | 1 | time axis 2025-04-02 to 2025-05-27
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-04-02 to 2025-05-27
TITLE 1
Task 1 | Goal | Name | 25% | 2025-04-01 | 3 | 2025-04-02: 2; 2025-04-03: 2
Task 2 | Milestone |  |  | 2025-04-06 | 1 | bar: 2025-04-06
Task 3 | Low Risk |  | 50% | 2025-03-29 | 10
Task 4 | Milestone |  |  | 2025-04-21 | 1 | bar: 2025-04-21
Task 5 | Med Risk |  | 10% | 2025-04-07 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-04-07 | 13
Task 2 | On Track |  | 50% | 2025-04-09 | 9
Task 3 | Low Risk |  | 33% | 2025-04-14 | 11
Task 4 | Milestone |  |  | 2025-04-16 | 1 | bar: 2025-04-16
Task 5 |  |  |  | 2025-04-17 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-04-16 | 4
Task 2 | Med Risk |  |  | 2025-04-19 | 14
Task 3 | On Track |  |  | 2025-05-04 | 6
Task 4 | Goal |  |  | 2025-05-08 | 3 | 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2
Task 5 | Low Risk |  |  | 2025-04-07 | 19
TITLE 4
Task 1 |  |  |  | 2025-05-11 | 15
Task 2 |  |  |  | 2025-05-25 | 5
Task 3 | Milestone |  |  | 2025-07-06 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2025-02-17 |  |  |  |  | March | [27 empty] | April
Scrolling Increment: | 16 | time axis 2025-03-05 to 2025-04-29
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Iteration 1
Complete All Activities in Iteration | Goal | Name | 100% | 2025-02-17 | 35 | W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2
Group Meeting Report | Low Risk |  | 100% | 2025-02-18 | 14
Stakeholder Registry | Med Risk |  | 100% | 2025-02-25 | 1
Persona | High Risk |  | 100% | 2025-03-04 | 2
Persona Review | Med Risk |  | 100% | 2025-03-10 | 1
Group Meeting Report 2 | Low Risk |  | 100% | 2025-03-17 | 7
Progress Report | Med Risk |  | 100% | 2025-03-18 | 2
Iteration 2
Complete All Activities in Iteration | Goal |  | 100% | 2025-03-24 | 9 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2
Resource table | Med Risk |  | 100% | 2025-03-25 | 1
Group Meeting Report 1 | Low Risk |  | 100% | 2025-03-25 | 7
Gantt Chart | Med Risk |  | 100% | 2025-03-31 | 2
Group Metting Report 2 | Low Risk |  | 100% | 2025-04-01 | 1
Progress Report | Low Risk |  | 100% | 2025-04-01 | 1
Iteration 3
Complete All Activities in Iteration | Goal |  | 0%
Group Meeting Report | Low Risk |  | 0%
Risk Register | On Track |  | 0%
Integrate Code, Push to GitHub, and Review Integration | Goal |  | 0%
Complete User Acceptance Testing | Low Risk |  | 0%
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2025-04-01 |  |  |  |  | April | [27 empty] | May
Scrolling Increment: | 5 | time axis 2025-04-06 to 2025-05-31
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-04-06 to 2025-05-31
TITLE 1
Task 1 | Goal | Name | 25% | 2025-04-01 | 3
Task 2 | Milestone |  |  | 2025-04-06 | 1 | bar: 2025-04-06
Task 3 | Low Risk |  | 50% | 2025-03-29 | 10
Task 4 | Milestone |  |  | 2025-04-21 | 1 | bar: 2025-04-21
Task 5 | Med Risk |  | 10% | 2025-04-07 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-04-07 | 13
Task 2 | On Track |  | 50% | 2025-04-09 | 9
Task 3 | Low Risk |  | 33% | 2025-04-14 | 11
Task 4 | Milestone |  |  | 2025-04-16 | 1 | bar: 2025-04-16
Task 5 |  |  |  | 2025-04-17 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-04-16 | 4
Task 2 | Med Risk |  |  | 2025-04-19 | 14
Task 3 | On Track |  |  | 2025-05-04 | 6
Task 4 | Goal |  |  | 2025-05-08 | 3 | 2025-05-08: 2; 2025-05-09: 2; 2025-05-10: 2
Task 5 | Low Risk |  |  | 2025-04-07 | 19
TITLE 4
Task 1 |  |  |  | 2025-05-11 | 15
Task 2 |  |  |  | 2025-05-25 | 5
Task 3 | Milestone |  |  | 2025-07-06 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one