## Dark
TungstenPC
TungstenPC |  | Members: |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gerard Yu
Project Start Date: | 2025-02-17 | Deacon Watt |  |  |  | April | [6 empty] | May | [27 empty] | June
Scrolling Increment: | 70 | Shawn Peipi | time axis 2025-04-28 to 2025-06-22
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Iteration 1
Complete All Activities in Iteration | Goal | All Members | 100% | 2025-02-17 | 35
Group Meeting Report | Med Risk | All Members | 100% | 2025-02-18 | 14
Stakeholder Registry | High Risk | All Members | 100% | 2025-02-25 | 1
Persona | Low Risk | All Members | 100% | 2025-03-04 | 2
Persona Review | Low Risk | All Members | 100% | 2025-03-10 | 1
Group Meeting Report 2 | Med Risk | All Members | 100% | 2025-03-17 | 1
Progress Report | Milestone | All Members | 100% | 2025-03-18 | 1
Iteration 2
Complete All Activities in Iteration | Goal | All Members | 100% | 2025-03-24 | 9
Resource table | Med Risk | Shawn,Deacon | 100% | 2025-03-25 | 1
Group Meeting Report 1 | Low Risk | Deacon,Gerard | 100% | 2025-03-25 | 7
Gantt Chart | Med Risk | Gerard | 100% | 2025-03-31 | 2
Group Metting Report 2 | Low Risk | Deacon | 100% | 2025-04-01 | 1
Progress Report | Milestone | Shawn | 100% | 2025-04-01 | 1
Iteration 3
Complete All Activities in Iteration | Goal | All Members | 0% | 2025-04-29 | 21 | T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2
Group Meeting Report | Med Risk | All members | 0% | 2025-04-29 | 1
Risk Register | Low Risk | All Members | 0% | 2025-04-29 | 7
Integrate Code, Push to GitHub, and Review Integration | Goal | All Members | 0% | 2025-05-13 | 7 | T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2
Complete User Acceptance Testing | Low Risk | All Members | 0% | 2025-05-13 | 7
To add more data, Insert new rows ABOVE this one

## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.